Studently Mobile App

14-Week Sprint Plan (one-week sprints)

Full app end to end: students, parents, teachers, QR scanner, librarian, inspector and admin on-the-go

Prepared for: Project Manager and the developer

Date: 2 October 2026

Version 2. Replaces the earlier 29-week, two-week-sprint plan. Status: Draft for review.

# Contents

1. Summary and reality check

2. What the app will do

3. Approach

4. Assumptions and weekly rhythm

5. Roadmap at a glance

6. Sprint-by-sprint details (Sprints 1 to 14)

7. Design alignment

8. Client inputs by week

9. Top risks

10. Store and compliance checklist

11. Reporting and early-warning rules

12. Appendix: audit findings and glossary

# 1. Summary and reality check

The goal is to deliver the whole Studently mobile app, for Android and iPhone, in 14 weeks, in 14 one-week sprints, built by one developer working with AI assistance. The app is one app with one sign-in: after login each person sees only the screens for their role.

## What is delivered

- Sign-in and security: username or email login, password reset, two-factor, biometric unlock, user agreement.

- Push notifications on real Android phones and iPhones.

- Student app, parent app and teacher app with all mandatory screens from the design brief.

- QR attendance scanner for gate and classroom use, working offline.

- Librarian, inspector and admin on-the-go screens, plus the school social wall.

- Store compliance: privacy policy, in-app account deletion, store listing and submission.

## Reality check

The earlier estimate for this same scope was about 29 weeks for a team of about five people. Delivering it in 14 weeks by one person is very aggressive, and the plan only works if the assumptions in section 4 hold. This plan does not remove scope. Instead it protects the date in four ways:

- Each sprint has two lists. "Must finish" is the acceptance test for the week. "Drop first if behind" is the order in which items are postponed if the week runs late. These are contingency options, not planned cuts.

- Week 14 is a buffer. It is used first for unfinished must-have items, then for hardening and handover.

- Efficiency measures. A ready-made mobile UI kit, screens built by pattern (lists, forms, detail pages, dashboards) so each pattern is built once, shared code reused from the website, AI-generated tests, and designs ready one week ahead of building.

- Early-warning rules (section 11). Weekly checks against the must-finish list and an escalation rule when two weeks in a row slip.

Not included in the 14 weeks: Apple and Google review time. Student and parent app is submitted in week 9, so its review overlaps weeks 10 and 11. The full app is submitted in week 13, so its review finishes after week 14.

## Main risks of this plan (see section 9)

- One person is a single point of failure: illness or a blocked week affects everything.

- There is no second reviewer, so automated tests and AI code review must replace peer review.

- Design must be ready one week ahead, otherwise building stalls.

- Switching between server, shared code and mobile work costs time every week.

# 2. What the app will do

Every screen is listed, with priority and states, in the separate Design Brief (119 screens, of which 86 are mandatory). Summary by user:

| User | Main features |
| --- | --- |
| Students | Home, timetable, attendance, grades and rank, report card, assignments with photo upload, quizzes, messages, complaints, fees, class diary, events, QR attendance card, library, Quran progress. |
| Parents | Child switcher, attendance, grades, homework, timetable, fees and receipts, messages, complaints, gate attendance history and excuse requests, child QR card, consent. |
| Teachers | Take attendance, timetable, class diary, assignments and grading, messages, discipline referrals, online classes, staff rotating QR code. |
| Gate staff and teachers (scanner) | Scan student cards at the gate or in class, offline, with duplicate protection, location check and automatic sync. |
| Librarians | Issue and return books by scan, search, loans and fines. |
| Inspectors | Visit list and visit report. |
| Administrators (on the go) | Live attendance, approvals, complaints, alerts and key figures. The full back office stays on the website. |

# 3. Approach

- One app for both phones. Built with React Native (Expo), so Android and iPhone are developed together.

- Reuse the existing server. About 85 to 90 percent of what students, parents and teachers need already exists on the server. About a dozen additions are required (listed in the sprints).

- Share logic, not screens. Data rules, menus, translations and server communication are moved into shared code used by both the website and the app. Screens are rebuilt for the phone.

- One repository. The app lives in the same project as the website and server so they change together.

- English and Arabic from the start, including right-to-left layout, light and dark mode.

# 4. Assumptions and weekly rhythm

## Assumptions that must hold

- Focused work of roughly 50 hours a week with AI-assisted development, and no extended absences.

- Designs (or a purchased mobile UI kit) are ready one week ahead of each build week.

- Secure server address, staging server with sample data, and Apple, Google and Firebase accounts are ready in week 1.

- A pilot school and students, parents and teachers for testing are available from week 7.

- The client answers decisions within two working days.

- No major rework: scope does not change during the 14 weeks.

- Definition of Done for every item: works on a real Android phone and a real iPhone, checked in English and Arabic, automatically tested, with no problem introduced on the website.

## Weekly rhythm (one-week sprints)

| Day | Activity |
| --- | --- |
| Monday | Plan the week: confirm the must-finish list; check designs for next week are ready (30 minutes). |
| Tuesday to Thursday | Build and test; short written progress note each day (what is done, what is blocked). |
| Thursday | Mid-week check: if the must-finish list is behind, start applying the "drop first" list. |
| Friday | Demo on real phones (recorded for the PM), retrospective, next week's design review, weekly update to the project manager. |
| Every second Friday | Demo to client stakeholders. |

# 5. Roadmap at a glance

| Milestone | Week | What is ready |
| --- | --- | --- |
| M0 Foundations | 2 | Shared project, user-profile and app-config services, design system |
| M1 Sign-in and notifications | 5 | Secure sign-in, two-factor, password reset, push on real phones |
| Alpha 1 | 7 | Student app in the hands of about five real students |
| Student and parent app submitted | 9 | Compliance complete, submitted to Apple and Google |
| Teacher app complete | 11 | Teacher mandatory screens and online classes |
| Full app submitted | 13 | Scanner, librarian, inspector, admin on-the-go and social wall; Beta 2 |
| Handover | 14 | Hardened, documented, rollback plan, final demo |

## Sprint calendar

| Sprint | Week | Theme | Milestone |
| --- | --- | --- | --- |
| 1 | 1 | Setup, shared foundations and decisions | Project start |
| 2 | 2 | Shared code, "who am I" service and design system | M0 Foundations complete |
| 3 | 3 | Sign-in |  |
| 4 | 4 | Security flows |  |
| 5 | 5 | App shell and push notifications | M1 Sign-in and notifications done |
| 6 | 6 | Student core screens |  |
| 7 | 7 | Student engagement and Alpha 1 | Alpha 1: internal test |
| 8 | 8 | Parent app |  |
| 9 | 9 | Parent extras, compliance and first store submission | Student + parent app submitted |
| 10 | 10 | Teacher part 1 and store response |  |
| 11 | 11 | Teacher part 2 and student and parent extras |  |
| 12 | 12 | QR scanner core and librarian |  |
| 13 | 13 | Scanner experience, inspector, admin, social wall and full submission | Full app submitted |
| 14 | 14 | Hardening, buffer and handover | Handover |

# 6. Sprint-by-sprint details

All 14 sprints use the same layout. Amber rows list what is postponed first if the week runs behind. Design runs one week ahead of building.

## Foundations (Sprints 1 to 2)

Sprint 1: Setup, shared foundations and decisions Week 1 ¦ Project start

| Sprint goal | - Remove every unknown and put the shared project structure in place so building can start at full speed in week 2. |
| --- | --- |
| Design needed this week | - Agree the visual direction: colours, type, icon style, and decide whether to buy a ready-made mobile UI kit or design from scratch. - Set up the design file structure (pages for foundations, components, each role, flows, asset export). - Start the app icon and splash screen concepts. - Convert the website palette into mobile colour tokens (light and dark). |
| Server (backend) work | - Confirm the live server has a secure (HTTPS) address with a valid certificate; fix before anything else if not. - Prepare a staging copy of the server and database with sample data for every role: student, parent, teacher, librarian, inspector, admin, gate staff. - Remove debug messages that print token fragments, key fingerprints and push addresses from server logs. - Write the list of server additions needed (push device tokens, user-profile service, forgot-password, own QR card, account deletion) and confirm each with the client. |
| Shared code work | - Create the shared project folders (data types, communication layer, helpers, scanner logic) and connect the website, server and mobile app in one repository. - Set up automatic build and type checks so a change for the app cannot silently break the website. - Merge the two conflicting copies of the shared data types (one is out of date and lacks a role). - Start the single shared server-communication client that replaces the 51 duplicated copies used by the website today. |
| Mobile app work | - Create the mobile app (Expo) with Android and iPhone builds. - Check the toolkit version works with the website's technology version and fix any conflict now. - Run four quick experiments: signing scanner requests on a phone, joining a video class, loading English and Arabic text, and the styling approach. - Open the Apple Developer, Google Play and Firebase (push notification) accounts. |
| Testing and quality | - Automatic checks run on every change (build, type check, existing website tests). - Blank app installed on one real Android phone and one real iPhone. - Record the results of the four experiments, with a fallback chosen for any that fail. |
| Demo at the end of the week | - Blank app opening on both phones; website unchanged; staging server reachable over a secure address; experiment results summary. |
| Must finish | - Secure server address confirmed. - Staging server with sample data for all roles ready. - Store and Firebase accounts opened. - Shared project builds for web and mobile. - Experiments finished with decisions recorded. |
| Drop first if behind | - Splash and icon concepts (move to week 3). - Fifth and later server list items (move to the week they are needed). |
| Needs from the client | - Client decisions: one school or several, final scope, secure server address. - Apple and Google developer account access. - Access to the server and database for staging. |
| Main risk and how it is handled | - The live server may not be secure, or the toolkit version may conflict with the website. Both would delay everything; they are tested in the first days of this week. |

Sprint 2: Shared code, "who am I" service and design system Week 2 ¦ M0 Foundations complete

| Sprint goal | - Move the website's reusable logic into shared code and build the two server services every screen depends on. |
| --- | --- |
| Design needed this week | - Design system version 1: about 20 core components (buttons, text fields, cards, list rows, chips, tab bar, sheets, toasts, skeletons) in English and Arabic, light and dark. - Navigation shell designs for each role. - Sign-in and password screens ready for build in week 3. |
| Server (backend) work | - Build the "who am I" service returning the user's profile, role, language, 2FA state, enabled school modules and branding. - Build the app configuration service: minimum app version, maintenance mode and feature switches. - Design the forgot-password flow with a link that opens the app. |
| Shared code work | - Move about 40 feature modules for all roles into the shared communication layer; isolate the 17 modules that use browser-only features behind small adapters. - Separate menu and role configuration from website visuals so the app can reuse it. - Move the English and Arabic translation files into the shared area and check they load in the mobile toolkit. - Share form-checking rules and date and format helpers. |
| Mobile app work | - Install the UI kit and apply the design tokens. - Language switching including right-to-left layout, with Arabic and English fonts. - Build the first reusable components and a gallery screen to review them on a phone. |
| Testing and quality | - Website regression run after every module move. - Check translation loading and right-to-left layout on real phones. - Test the new services on staging with each role. |
| Demo at the end of the week | - Component gallery on both phones in English and Arabic; website running on the shared code; the "who am I" response for each role. |
| Must finish | - "Who am I" and app configuration services live on staging. - At least half of the modules used by the website run on the shared communication layer. - Design system approved. |
| Drop first if behind | - Modules for librarian, inspector and admin (move later in the plan). - Dark mode polish. |
| Needs from the client | - Designer or UI kit decision from week 1. - Test accounts for each role. |
| Main risk and how it is handled | - Moving shared code could break the website. Handled by moving one module at a time with automatic checks. |

## Sign-in, security and notifications (Sprints 3 to 5)

Sprint 3: Sign-in Week 3

| Sprint goal | - A user can sign in, stay signed in securely, and recover a forgotten password. |
| --- | --- |
| Design needed this week | - Final sign-in, school selection, language selection and system screens (no connection, session expired, update required, maintenance). - Splash screen and app icon final versions. - Forgot-password and reset-password screens with strength meter. |
| Server (backend) work | - Forgot-password and reset-password service with an emailed link that opens the app. - Limit repeated attempts on the username lookup and password change so they cannot be abused; stop the username lookup from revealing which usernames exist. - Make the school lookup work for several schools if the client chose that. |
| Shared code work | - Shared sign-in helpers: username to email lookup, session state, handling of the special server messages (suspended, trial expired, agreement rejected, two-factor required). |
| Mobile app work | - Sign-in screen with username or email, password with show/hide, remember device, and school branding and background. - Secure session storage on the phone (no passwords saved in plain text) and automatic session refresh. - Forgot and reset password screens with deep link return. - System screens, language selection, school selection, splash and app icon in place. |
| Testing and quality | - Test sign-in with a student, a parent, a teacher and an admin on both phones. - Wrong password, inactive account and no-connection cases. - Reset link opens the app on both platforms. |
| Demo at the end of the week | - Sign in and out; reset a password through an emailed link; switch language. |
| Must finish | - Sign-in works for all roles on Android and iPhone. - Session survives app restart and refreshes automatically. - Password reset works end to end. |
| Drop first if behind | - School selection screen if the app serves one school. - Remember device option. |
| Needs from the client | - Working email delivery on staging; test accounts. |
| Main risk and how it is handled | - Reset link not opening the app on one platform. Tested on the first day with real devices. |

Sprint 4: Security flows Week 4

| Sprint goal | - Complete every security step the web already has: two-factor, agreement, forced password change and account state messages. |
| --- | --- |
| Design needed this week | - Two-factor code, recovery and three-step setup screens. - Biometric unlock and permission prompts. - User agreement (accept, reject, blocked student, read view), forced password change, suspended, trial-expired and reactivate screens. |
| Server (backend) work | - Check whether two-factor verification expires with the sign-in token and fix it so users are not asked every hour. - Add attempt limits to two-factor code and recovery code entry. - Make sure the agreement and force-change rules are returned clearly in the "who am I" service. |
| Shared code work | - Shared two-factor and agreement state logic used by web and app. |
| Mobile app work | - Two-factor code entry, recovery code, and setup (scan or copy secret, confirm code, save recovery code). - Biometric unlock (fingerprint or face) with password fallback. - User agreement flow including the parent accepts-for-student block and reject-then-sign-out. - Forced password change, suspended and trial-expired screens, session-expired handling, account reactivation. |
| Testing and quality | - Test every state with a dedicated test account: 2FA on, agreement pending, account suspended, trial expired, must change password. - Verify tokens persist across 24 hours without extra prompts. - Arabic layout check on all new screens. |
| Demo at the end of the week | - A two-factor user signs in with biometrics; an agreement is accepted; a suspended school shows the right message. |
| Must finish | - All sign-in and security states work on both platforms. - No repeated hourly two-factor prompts. - Nothing sensitive stored in plain text. |
| Drop first if behind | - Reactivate account screen. - Biometric option for roles other than parents and teachers. |
| Needs from the client | - Test accounts for each security state. |
| Main risk and how it is handled | - Two-factor session behaviour may differ from what the audit assumed. Tested on day one, with a server fix if needed. |

Sprint 5: App shell and push notifications Week 5 ¦ M1 Sign-in and notifications done

| Sprint goal | - The app has its navigation, school branding and receives push notifications on real Android phones and iPhones. |
| --- | --- |
| Design needed this week | - Tab bar for each role, school logo frames (circle, rounded, square, rectangle), child switcher. - Notification inbox and permission prompt. - Notification icon and empty and error illustrations. - Student home and timetable designs for week 6. |
| Server (backend) work | - Add phone push support (today only website push exists): store device tokens, register and unregister endpoints, send through Google and Apple, clean up invalid tokens. - Add campus targeting to the "send to a role" function. - Publish the files that let web links open the app directly. - Add the first push triggers: messages, absences, assignments due, grades posted. |
| Shared code work | - Shared notification type definitions and deep-link route mapping. |
| Mobile app work | - Role-based tab bar and navigation for every role, hiding modules the school has switched off. - School logo and branding on every header. - Child switcher shell for parents. - Notification permission flow, registering the phone, receiving, tapping to open the right screen, and the notification inbox. |
| Testing and quality | - Test push delivery on one Android and one iPhone, app open, in background and closed. - Wrong or revoked token handling. - Menus verified for each role and for a school with modules off. |
| Demo at the end of the week | - Send a test notification from the admin panel; it arrives and opens the right screen on both phones. |
| Must finish | - Push works on real Android and iPhone. - Each role sees its own tabs. - Branding appears correctly. |
| Drop first if behind | - Extra push triggers beyond messages and absences. - Campus targeting. |
| Needs from the client | - Apple push key and Firebase credentials from week 1. |
| Main risk and how it is handled | - Apple push setup is often slow. Credentials were requested in week 1; a fallback through Expo push is available. |

## Student and parent app (Sprints 6 to 9)

Sprint 6: Student core screens Week 6

| Sprint goal | - A student can see their whole school day and academic progress. |
| --- | --- |
| Design needed this week | - Student screens: home, timetable, attendance, grades, report card, diary, events, profile with all states. - Charts: attendance ring, grade bars. - Student assignment, quiz and messaging designs for week 7. |
| Server (backend) work | - Rewrite the slow class-rank calculation so it responds in under half a second for a 40-student class. - Clamp list sizes and add paging on long lists. - Add extra role protection on every student route. - Add the report-card download in a form a phone can open. |
| Shared code work | - Student data modules and hooks reused from the website; shared date, academic-year and grade-band helpers. |
| Mobile app work | - Home: greeting, term, attendance, today's classes, assignments due, fees, weather. - Today's and week timetable with period states. - Attendance summary, calendar and by-subject detail. - Grades overview and by subject, GPA and rank, report card viewer, class diary, events and calendar, profile. |
| Testing and quality | - Test with a student who has full data and one with none (empty states). - English and Arabic; light and dark; one small phone. - Speed check of the rank service. |
| Demo at the end of the week | - A student walks through every core screen on staging data in both languages. |
| Must finish | - All student core screens work with loading, empty and error states. - Rank service meets speed target. |
| Drop first if behind | - GPA trend chart. - Weather widget. - Add-to-phone-calendar. |
| Needs from the client | - Realistic staging data for at least two students. |
| Main risk and how it is handled | - Slow screens on low-end Android phones. Checked on a low-end device at the end of the week. |

Sprint 7: Student engagement and Alpha 1 Week 7 ¦ Alpha 1: internal test

| Sprint goal | - A student can submit work, take quizzes, message teachers, see fees and show a QR attendance card; put the first build in real students' hands. |
| --- | --- |
| Design needed this week | - Assignments (list, detail, submit), quizzes, messages, complaints, fees, polls and notes, QR attendance card. - Parent home and child switcher designs for week 8. |
| Server (backend) work | - Build the self-service QR card service so students (and parents for their children) can fetch their own signed card; today only admins can. - Set longer time limits and size limits for uploads on weak mobile connections. - Add push triggers for new messages and posted grades if not done. |
| Shared code work | - Shared upload helper for photos and files; messaging, complaints and fee modules moved to the shared layer. |
| Mobile app work | - Assignments list, detail and submit with text, photo and file upload. - Quizzes with timer and result. - Messages: inbox, thread, compose with attachments and templates. - Complaints list, submit and thread; polls and notes; fees and payment history. - QR attendance card with brightness boost. |
| Testing and quality | - Upload tests on slow and interrupted connections. - Quiz timer and leave-warning tests. - Alpha build to about five students at a pilot school through TestFlight and Google Play internal testing. |
| Demo at the end of the week | - A student submits an assignment with a photo, sends a message and shows their QR card; Alpha 1 installed on real phones. |
| Must finish | - All student mandatory screens done. - QR card service live. - Alpha installed by real students and feedback list started. |
| Drop first if behind | - Polls and notes. - Message templates. - Quiz review screen. |
| Needs from the client | - Pilot school agreement and student volunteers. |
| Main risk and how it is handled | - Uploads failing on weak networks. Tested with throttled connections before the Alpha. |

Sprint 8: Parent app Week 8

| Sprint goal | - A parent sees accurate, private information for each of their children. |
| --- | --- |
| Design needed this week | - Parent screens: attendance, grades, homework, timetable, exams, fees, receipts, discipline, activities, diary, messages, complaints. - Compliance screens for week 9: settings, account deletion, privacy. - Store screenshots plan. |
| Server (backend) work | - Audit every parent service so a parent can only ever see their own children's data; fix every gap found. - Fix the slow multi-step queries in parent grades and homework. - Add push for absences and fee reminders. |
| Shared code work | - Parent modules and the child-switching logic shared with the website; contract tests for parent services. |
| Mobile app work | - Parent home with the selected child card and quick tiles. - Child switcher (remembers last choice). - Child profile, attendance, grades and gradebook, homework (view only), timetable, exams. - Fees, payment history and receipt, discipline, activities, class diary. - Messages and complaints for parents. |
| Testing and quality | - Privacy tests: another family's child ID must return nothing, on every parent service. - Test with a parent with one, two and zero children. - English and Arabic; light and dark. |
| Demo at the end of the week | - A parent with two children switches between them and sees correct data; a blocked attempt on another family's child. |
| Must finish | - Privacy tests pass on every parent service. - All parent mandatory screens work. |
| Drop first if behind | - Activities screen. - Discipline screen. - Exam results detail. |
| Needs from the client | - Test families with several children and different fee states. |
| Main risk and how it is handled | - Privacy gaps in parent data access. This is the most serious risk in the project and is tested before any parent build is shared. |

Sprint 9: Parent extras, compliance and first store submission Week 9 ¦ Student + parent app submitted

| Sprint goal | - Finish the student and parent app, meet App Store and Google Play rules, and submit it. |
| --- | --- |
| Design needed this week | - Settings, notification preferences, account-deletion request, privacy policy link. - Store screenshots in English and Arabic, store graphics. - Teacher home and attendance designs for week 10. |
| Server (backend) work | - Account-deletion request and anonymising process with an admin workflow. - Public privacy policy and terms pages for the platform. - Consistent error messages and codes on all services the app uses. |
| Shared code work | - Contract tests for final student and parent services. |
| Mobile app work | - Gate attendance history and excuse request for parents. - Child QR card and ID card, school information and pages, photo consent, notification settings per child. - Settings screen (language, theme, biometrics, notifications, privacy, version) and account-deletion request. - Crash reporting, accessibility pass and performance tuning. - Store listing, privacy and data-safety forms, review notes with test accounts. |
| Testing and quality | - Full run through every student and parent screen on both platforms. - Screen reader and large-text checks. - Beta 1 with 2 to 3 pilot schools. |
| Demo at the end of the week | - Beta 1 in use at pilot schools; store submissions made for both platforms. |
| Must finish | - Account deletion and privacy policy in place. - Store materials complete. - Student and parent build submitted to both stores. |
| Drop first if behind | - Photo consent. - School pages. - ID card (QR card is enough). |
| Needs from the client | - Privacy policy text and account-deletion policy from the client. - Pilot schools. |
| Main risk and how it is handled | - Store rejection for missing deletion or privacy items. Both are done this week before submitting. |

## Teacher app and extras (Sprints 10 to 11)

Sprint 10: Teacher part 1 and store response Week 10

| Sprint goal | - A teacher can see their day and take attendance; handle store review and roll out gradually. |
| --- | --- |
| Design needed this week | - Teacher home, timetable, class list, student profile, take-attendance flow with all states. - Teacher diary and assignment designs for week 11. |
| Server (backend) work | - Teacher summary service for the home screen (classes, pending attendance, work to grade, unread messages). - Review role protection on every teacher route. - Handle any store review feedback that needs a server change. |
| Shared code work | - Teacher attendance, timetable and student modules shared. |
| Mobile app work | - Respond to store review comments and release gradually (10 percent, then more). - Teacher home, timetable (current and next class), class list, student list and profile. - Take attendance: class and date picker, tap to cycle present, absent, late, mark all, comments, counts, save, view-only outside the allowed window, bulk update. |
| Testing and quality | - Attendance edge cases: edit window closed, offline, unsaved changes, large class. - Test with teachers on real devices; English and Arabic. - Monitor crash reports from the first live users. |
| Demo at the end of the week | - A teacher takes attendance for a class and the saved data appears for the parent. |
| Must finish | - Teacher home and take attendance work end to end. - Release 1 rollout underway with no critical issues. |
| Drop first if behind | - Teacher timetable week view. - Student profile detail. |
| Needs from the client | - Teacher test accounts and timetables; store review responses. |
| Main risk and how it is handled | - Store review questions pulling time away. Time is reserved in this week for responses. |

Sprint 11: Teacher part 2 and student and parent extras Week 11

| Sprint goal | - A teacher can run the rest of the class day; add the extra learning features for students and parents. |
| --- | --- |
| Design needed this week | - Class diary, create assignment, submissions list, grading sheet, discipline referral, online class, events, staff rotating code. - E-library and Quran progress screens. - Scanner designs (all result states) for week 12. |
| Server (backend) work | - Teacher messaging recipient rules check. - Any missing services for grading on a phone. - Push for events and announcements. |
| Shared code work | - Teacher assignment, diary, grading and discipline modules shared. |
| Mobile app work | - Class diary list and new entry. - Create and edit assignments with attachments and due dates; submissions list and grading sheet with score and feedback. - Teacher messaging, discipline referral, complaints, events. - Online class join (needs a special build), staff rotating QR code. - E-library and Quran progress for students and parents. |
| Testing and quality | - Full class-day run: attendance, diary, assignment, grading, parent sees result. - Online class on two phones. - Large attachment upload tests. |
| Demo at the end of the week | - Teacher creates an assignment, a student submits, the teacher grades, the student sees the grade. |
| Must finish | - Teacher mandatory screens complete. - Staff rotating code works. |
| Drop first if behind | - Quran progress. - E-library. - Discipline referral. |
| Needs from the client | - Online class test room. - Sample books for e-library. |
| Main risk and how it is handled | - Video class needs a special build and device testing. The experiment from week 1 reduces this risk. |

## Scanner, other roles and full submission (Sprints 12 to 13)

Sprint 12: QR scanner core and librarian Week 12

| Sprint goal | - Bring the existing QR attendance scanner into the app, working offline, and add the librarian flows that use scanning. |
| --- | --- |
| Design needed this week | - Scanner result states (accepted check-in, check-out, duplicate, rejected variants), permission screens, offline banner, enrolment. - Librarian issue, return and search screens. - Inspector and admin on-the-go designs for week 13. |
| Server (backend) work | - Compatibility tests proving signatures from a phone are accepted. - Limit device enrolment attempts and remove sensitive logging in the scanner service. - Check live attendance update load. |
| Shared code work | - Extract the scanner rules into a shared package: card checking, location boundary, duplicate protection and sync retry, with the existing tests moved over. |
| Mobile app work | - Secure signing and key storage on the phone. - Offline queue that keeps scans and photos if the app closes. - Device enrolment screen with one-time code. - Camera and location permission screens. - Librarian issue and return by scan, book search, loans and fines. |
| Testing and quality | - Signature test against the live server. - Queue survives app kill and phone restart. - Librarian flows with real barcodes or QR codes. |
| Demo at the end of the week | - A card scanned offline syncs and the server accepts it; a librarian issues and returns a book. |
| Must finish | - Scanner logic shared and signature accepted by the server. - Offline queue reliable. - Device enrolment works. |
| Drop first if behind | - Loans and fines list. - Photo capture queue. |
| Needs from the client | - Enrolment codes and a pilot school admin; sample library data. |
| Main risk and how it is handled | - Phone security tools may not match the server's signature format. The week-1 experiment chose a fallback (small custom component). |

Sprint 13: Scanner experience, inspector, admin, social wall and full submission Week 13 ¦ Full app submitted

| Sprint goal | - Finish every remaining role and screen, test the scanner for real conditions, and submit the full app. |
| --- | --- |
| Design needed this week | - Inspector visit list and report, admin live attendance, approvals, complaints, alerts, key figures, school social wall. - Polish pass and refreshed store screenshots. |
| Server (backend) work | - Photo upload limits and load check for live attendance updates. - Inspector and admin summary services if missing. - Any server fixes from Beta 1 feedback. |
| Shared code work | - Inspector, admin and social modules shared. |
| Mobile app work | - Gate and class scan screens with result overlays, sound and vibration, screen-awake, fake-GPS and location boundary check, offline banner, sync status, background sync, staff code check. - Inspector visit list and report. - Admin live attendance, approvals, complaints, alerts and key figures. - School social wall (viewing first). - Beta 2 at a pilot school; submit full build to both stores. |
| Testing and quality | - 48-hour offline test, airplane mode, clock difference, low-end Android. - Role regression: sign in as every role and check menus. - Store submission checklist. |
| Demo at the end of the week | - Gate staff scan cards with the phone offline; admin sees them on live attendance; full app submitted. |
| Must finish | - Scanner passes the offline tests. - All remaining roles have their mandatory screens. - Full build submitted. |
| Drop first if behind | - Social wall. - Admin key figures dashboard. - Inspector report photos. |
| Needs from the client | - Pilot school with scanning devices; store account access. |
| Main risk and how it is handled | - Too much remaining scope for one week. Drop list is applied from Wednesday if progress is behind. |

## Hardening and handover (Sprint 14)

Sprint 14: Hardening, buffer and handover Week 14 ¦ Handover

| Sprint goal | - Make the app secure, fast and supportable, finish anything that slipped, and hand over. |
| --- | --- |
| Design needed this week | - Final accessibility and Arabic typography fixes. - Final store assets and any fixes from review feedback. |
| Server (backend) work | - Security review of the new services and of stored sensitive data (including reversible passwords and what the profile service can return). - Make fee and accounting attachments private. - Decide on Google and Microsoft sign-in for the app. - Faster sign-in checks if time allows. |
| Shared code work | - Reduce app size by splitting translation files; documentation for the shared packages. |
| Mobile app work | - Start-up under 2.5 seconds on a mid-range Android phone, image caching and list speed. - Fix Beta 1 and Beta 2 feedback. - Monitoring and crash dashboards, update policy, rollback plan. - Runbook and support documents; final demo and handover. |
| Testing and quality | - Full end-to-end test on every role and both platforms. - Security checks on new services. - Re-test any fixed defects. |
| Demo at the end of the week | - Final demo of the complete app and handover pack. |
| Must finish | - No critical or high defects open. - Handover documents done. - Rollback plan documented. |
| Drop first if behind | - Google and Microsoft sign-in. - Faster sign-in checks. |
| Needs from the client | - Client sign-off; budget for an external security review if wanted. |
| Main risk and how it is handled | - Slipped work from earlier weeks. This week is the planned buffer, so it is used first for unfinished must-have items. |

# 7. Design alignment

Design runs one week ahead. The design brief lists every screen; this table shows when each group must be ready.

| Ready before | Design deliverable | Notes |
| --- | --- | --- |
| Week 1 (during) | Direction, tokens, UI kit decision, file structure | Icon and splash concepts |
| Week 2 | Design system v1 (about 20 components), navigation shell | English, Arabic, light, dark |
| Week 3 | Sign-in, password, system screens, final icon and splash | Top 12 screens: sign-in first |
| Week 4 | Two-factor, agreement, biometric, forced password change, account state screens |  |
| Week 5 | Tab bars, branding, child switcher, notification inbox, illustrations | Notification icon |
| Week 6 | Student core screens | Student home, timetable, attendance, grades |
| Week 7 | Student engagement screens, QR card | Assignments, messages, fees, QR card |
| Week 8 | Parent screens | Parent home with child switcher |
| Week 9 | Settings, deletion, privacy; store screenshots and graphics | English and Arabic |
| Week 10 | Teacher home and take attendance |  |
| Week 11 | Teacher diary, assignments, grading; e-library and Quran |  |
| Week 12 | Scanner states, librarian screens | Includes sound and vibration spec |
| Week 13 | Inspector, admin on-the-go, social wall, polish |  |
| Week 14 | Accessibility and Arabic fixes, final store assets |  |

# 8. Client inputs by week

| Week | Needed from the client | Why |
| --- | --- | --- |
| 1 | Secure server address; single or multiple schools; scope sign-off; Apple, Google and Firebase accounts; server and database access | Unblocks every later week |
| 1 to 2 | Test accounts for every role; sample data | Needed for all testing |
| 3 | Working email delivery on staging | Password reset |
| 5 | Apple push key and Firebase credentials | Push notifications |
| 7 | Pilot school and student volunteers | Alpha 1 |
| 8 | Test families with several children | Parent privacy testing |
| 9 | Privacy policy text; account-deletion policy; pilot schools | Store requirements |
| 11 | Online class test room; sample library books | Teacher and library testing |
| 12 | Scanner enrolment codes; school admin; sample library data | Scanner and librarian |
| 13 | Pilot school with scanning devices | Beta 2 |
| 14 | Sign-off; optional external security review | Handover |

# 9. Top risks

| Risk | What could happen | How it is handled |
| --- | --- | --- |
| Single developer | Illness or a blocked week delays everything | Daily written notes, automated tests, buffer week 14, escalate after two slipped weeks |
| Scope vs 14 weeks | The full scope may not fit | Must-finish and drop-first lists each week; weekly burn-up reporting |
| Server not on a secure address | Apple and Google block the app | Confirmed in week 1 |
| Design not ready | Building stalls | Design runs one week ahead; UI kit as a fallback |
| Parent privacy gaps | A parent could see another family's data | Full audit and negative tests in week 8 |
| Scanner signatures | The server rejects scans from phones | Experiment in week 1; tests in week 12 |
| Store rejection or delay | Launch dates move | Compliance in week 9; early submission of student and parent app |
| Slow or weak connections | Uploads and screens fail in the field | Throttled-connection testing; upload limits changed in week 7 |
| Unsupported features | Video class needs a special build | Experiment in week 1; fallback to opening the class in a browser |

# 10. Store and compliance checklist

- Public privacy policy and terms of use page (week 9).

- In-app account-deletion request and server process (week 9).

- Accurate privacy and data-safety forms: camera, location (scanner), photos, and data about minors.

- Secure (HTTPS) connections only.

- No in-app payments exist, so store in-app purchase rules do not apply. Re-check if online payment is added later.

- Store listing, screenshots in English and Arabic, review notes and test accounts including a two-factor account.

- Accessibility and right-to-left review.

- Security items to resolve before wide release: stored reversible passwords, public fee and accounting attachments (week 14), missing limits on repeated login attempts (weeks 3 and 4).

# 11. Reporting and early-warning rules

## Weekly report to the project manager

- Must-finish list: done, partly done, not done.

- Screens completed against the 119 in the design brief and the 86 mandatory.

- Burn-up chart of screens and server items.

- Defects by severity and crash-free sessions (target 99 percent or more after launch).

- Items moved by the "drop first" list and why.

- Next week's design readiness.

## Early-warning rules

- Amber: one must-finish item missed in a week. Decide on Monday whether to recover it or move it.

- Red: two weeks in a row with missed must-finish items, or any sprint in which the drop-first list was fully used. The PM and client must decide on options within two days: extra help, a design or UI-kit change, or a date change.

- Never skip the parent privacy tests (week 8) or the store compliance items (week 9) to save time.

# 12. Appendix

## A. What the system audit found

| Area | Finding |
| --- | --- |
| Server | Ready for mobile in its design (uses secure tokens, nothing tied to a browser). Needs about a dozen additions: phone push, user-profile service, app config, forgot-password, own QR card, account deletion, school lookup, limits on repeated attempts, and performance fixes. |
| Website | About 750 pages. Screens cannot be reused, but data definitions, menus, translations and server-communication code can be shared. |
| QR scanner | The existing web scanner works offline. Its rules can be reused; camera, storage and security parts must be rebuilt for the phone. |
| Notifications | Only website notifications exist today. |
| Login | Forgot-password does not exist and must be added. Two-factor exists and must be supported. |
| Payments | No online payment, so store payment rules do not apply. |
| Privacy and security | No self-service account deletion or platform privacy policy; some sensitive data handling needs review. |

## B. Glossary

| Term | Meaning |
| --- | --- |
| Server (backend) | The part that stores data and applies the rules. The website and app both use it. |
| Shared code | Code used by both website and app so they behave the same. |
| Push notification | A message delivered to a phone even when the app is closed. |
| HTTPS | A secure web address required by Apple and Google. |
| Two-factor (2FA) | A second sign-in step using a code from an authenticator app. |
| Staging | A safe test copy of the system with sample data. |
| Alpha / Beta | Alpha is an internal test; Beta is a wider test at pilot schools. |
| TestFlight / Play internal testing | Official ways to give testers pre-release builds. |
| Phased rollout | Publishing to a small percentage of users first. |
| UI kit | A ready-made set of mobile screen components that speeds up design and build. |
| QR card | A signed QR code that identifies a student or staff member at the gate or classroom. |
| Right-to-left (RTL) | Mirrored layout used for Arabic. |